## Scope of work
Auditing Company - Customer Website Application |  |  |  |  | Website | Testing
S.NO | SCREEN NAME | FEATURE/SCREEN DETAILS |  | ADDITIONAL REMARKS
1 | PHASE I: DOCUMENTATION | FSD: Functional Specification Document | Project Plan
2 | PHASE II: DATABASE | Database Design |  |  | 100
3 | PHASE III: DESIGN | Inner & Outer Pages Designing | HTML Mobile Responsive
4 | PHASE IV: CODE DEVELOPMENT | Types of Users: There will be 3 different types of users who will be interacting with the website. | Client/Company : [Who are being audited ] .Who will upload all the required document of their company employees, get updates and audited documents. | Website
|  |  | Auditor: [Contractors] Who will get the auditing request from admin and work on that by updating status. | Website
|  |  | Admin : Owner of the portal who will manage clients/Companys, auditor and entire portal data. | Web panel
5 | PHASE V: TESTING | Testing | Debugging
6 | PHASE VI: DEPLOYMENT | Deployment over Respective server.
7 | PHASE VII: MAINTENANCE | Complimentary Bug Removal Period for 60 days
| 3rd Party API | 1. Payment gateway [ STRIPE ] 3.Docu sign, hello sign API | 4. Chat API 5. Accounting Software -MYOB [MYOB API will be used for generating the invoice to client and store the invoice calculation and data] | Language : English Only | 200
User Mode : Client /Company (Website)
1 | Login | 1. User name 2. Password | Login [Button] Remember me ¦Forgot Password | Note : There will be 3- 5 clients of the company , so admin will provide the login credientials to all. | 4
2 | Home Screen /Dashboard | Tabs / Menu Bar - 1. My Account 2. Notification 3. History 4. Login [Button] | Request New Audit [Button]---> Redirect to Request page. Chat [Button ] --> After click respective chat window will open | Note : 1. There will be a chat between Auditor and client/company. Action : [Questions, answers, clarifications] | 30
3 | Audit Request page | A.Stage 1 for both [verification and certification] 1. Select Audit Type [verification or certification] 2. Input Details about company [text box](eg: (size, activity, etc.) 3. View calendar [Available audit dates] a. Select Date / Week/ Time 4.View all company staff list [Xls sheet] Action : View Required documents need to upload for audit staff [Refer sheet 2 [Document list Bist] for document list] a. Upload Documents [via OCR] b. Enter Expiry date | c. Upload additional document [if any , that are not in a list] [Client have to upload all individual staff document for audit] Confirm and Book Audit [Button] B. Stage 2 [Only for Certification] 1. View Required Document to upload a. Upload document with expiry date 2. View calendar [Available audit dates] a. Select Date / Week Change Audit date [Button] --> Request goes to admin [If accepted --> Pay fee [Via payment gateway]] | Note : 1. Available audit dates calendar will be visible till date is booked, after that it will not be visible. 2.Documents are checked / pre-approved by the app--> If the document is expired, the client cannot submit it 3. Stage 2 will be done physical by the auditor and document are uploaded on the portal. 4. This page will also include the new audits that are created by admin, after that client have to fill the details required details in form. 5. Document format can be PDF, JPG, JPEG, PNG, GIF, TIF, XLS, XLSX, DOC, DOCX, PPT, PPTX | 16
4 | Audit History /Reports | View New / past history Details : 1. Audit Type [Verification /certification] 2. Applied Date and time 3. Auditor name [Who works on that] 4. View selected audit calendar date 5. View all uploaded documents . a. For Audit staff b. For company 6. View Audit Report [Uploaded by auditor] - For stage 1 and 2 | Action : a. Approve --> Go to next step b. Reject Report 1. Write Reason [text] c. Make payment [via payment gateway] -> If report is final. Status : 1.Pending / completed /Verification process/ Rejected/Approved 2. For certification :Stage 1 complete , Stage 2 complete | Note : Client have to submit the Final payment within 5 business days after report is approved by them | 32
5 | Invoice History | 1. View New Invoice a. Invoice ID b. Amount 1. Total Deposit 2. Need to pay c. View SLA Action : 1. View/ Sign the SLA and Send 2. View and pay Deposit a. Select Mode [Credit card/ bank/ PayID/BPay TBC] | 2. View Past Invoice a. Invoice ID b. Date and time c. Audit Details [Type, Auditor name] d. Signed SLA e. Paid Deposit amount[X] Action : Download Document [Invoice , SLA , Report] | Note : 1. Client can only download the documents , that can not export it | 32
6 | My Account | 1. Manage Profile - View / add/edit/delete/activate/deactivate a. Profile information [Name, e-mail address, contact number, company Name/address/ABN] b. Change password 2. Upload Company details : a. Documents: View all documents list need to upload [Refer sheet 2 (documnet list bist) for document list] b. Manage - Upload /View /Edit/delete Staff Sheet Data [xls sheet] | 3. Transaction History : a. Transaction ID b. Transaction Type [Audit Payment / change date fee/ Deposit amount] c. Amount fee[X usd] d.Transaction Date and time Notification : 1. Document uploaded successfully 2. Request to upload new document from admin 3. Your audit has completed , waiting for the report 4. New Report generated 5. Final Report uploaded by auditor | 6. Stage 1 complete for certification process . Apply for Physical audit (2nd stage) [Button] -->Redirect to apply screen 7. Stage 2 request has accepted or rejected by the admin. 8. Stage 2 has completed and audit report uploaded by auditor 9. New Audit created by admin --> Go to Audit request page [will redirect to respective page] 4.Content screen : a. Resource documents b. Terms and condition c. Privacy Policy d. FAQ e. About us | 20
User Mode : Auditor (Website)
1 | Login | 1. User name 2. Password | Login [Button] Remember me ¦Forgot Password |  | 4
2 | Dashboard | Data- Today , Weekly , Monthly 1. Total Auditing Clients a. New/ Past 2. Total Auditings: a. On going [Stage name] 1. Progress status a. Stage [1 or 2] | b. Done /completed c. Not completed d. Rejected 3. Total Audit type done a. Verification b. Certification 4. Total report generated | Filter by : Weekly /Monthly /Yearly | 30
3 | Manage Audits | A.View New 1. Client/Company name a. Staff sheet [Attached] 2. E-mail Address and contact Number 3. Audit Type [Verification / Certification] 4. Selected Audit day/ date 5. View Uploaded documents Action : 1. View and Approve / Reject Client/company Documents a. Request to add additional document 2. Upload New Report [pdf] a. To Client 3. Amend Report | B. On-going /Current 1. Client /Company name 2. Select Audit Type [Verification / Certification] a. List of certification Audits planned and dates 1. List of stage 1 Action : a. Mark as complete b. Send additional document request for stage 2 [select doc from list] 2. List of stage 2 b. List of verification audits planned and the week 3. Status : Completed / Pending Action: Upload new report [Pdf] C. View Rejected Reports : Action : Review and Upload final | D Past : 1. Client/Company name 2. E-mail Address and contact number 3. Audit Type [Verification / Certification] 4. View documents and Reports [Uploaded /shared] 5. Status [Completed / Pending] Note : 1. New Audit requirements will be given by admin to them. 2.All documents uploaded are deleted within 6 months after report is submitted to AU Gov 3. Report will be sent to AU govt Out of the website / Portal. | 30
4 | Notification | 1. Successfully login in the portal 2. New Audit request received 3. Send Audit Report successfully [Stage 1 and stage 2] 4.Report Accept / reject by client [Stage 1and stage 2] | 5.Audit date has changed by the admin [Audit type and date] 6.Got Chat Request [After click respective window will open] 7. New Updates from admin a. Upload document b. Policy change Updates |  | 16
5 | My Account | 1. Manage Profile - View / edit a. Profile information [Name, e-mail address, contact number, company Name] b. Change password [will need the permission of admin] | 2.Content screen : a. Resource documents b. Terms and condition c. Privacy Policy | Note : Auditor will be paid by the admin out of the portal | 16
Admin [Web panel]
1 | Login | 1. User name 2. Password | Login [Button] Remember me ¦Forgot Password |  | 4
2 | Dashboard | A. Data- Today , Weekly , Monthly 1. Total Registered Clients a. Active --> At what stage of auditing b. Inactive 2. Total Registered Auditors 3. View calendar Audits | 4. Total Auditing Report a. Successfully Completed b. Pending /On-going 5.Total Revenue / earning : a. From the new audting b. From date change fee of existing c. After deducting auditor payment | Filter by : Weekly /Monthly /Yearly | 16
3 | Manage Clients/Company | Admin can manage (view/add/edit/delete/activate/deactivate)the clients Search By : Name Add New client/Company : 1. Company Name 2. E-mail Address | 3. Contact number 4. Company Address 5. Company ABN Add [Button] | Note : Admin will provide the login credentials to users(Clients, Auditors), with which they can login or use the app. | 16
4 | Manage Auditors | Admin will manage (view/add/edit/delete/activate/deactivate)the Auditors Search By : Name and Experience A. Add New Auditors : 1. Name 2. E-mail Address 3. Contact Number | 4. Experience 5. Company Name Add [Button] B. Request for some document to upload 1. Select Auditor 2. Select document type [via tick] Send [Button] |  | 32
5 | Manage Auditors Calendar | Admin can manage (View/ add/edit / delete) the auditors calendar. A. View Auditors Calendar 1. View total Available auditors with time slots. 2. Filter by : verification / certification --> Audit Verification - Per weeks (eg: w/c 25th Jan, w/c 1st Feb, etc.) ---> Audit Certification - per day | B. Add Availability based on the schedule 1. Select Auditor name [from dropdown] 2. Select Available date / day / time slot Update [Button] |  | 40
6 | Manage all Audits Request | Audit type : New / Past 1. New Audit Request Details : Type - Stage 1 a. Audit type [Verification / Certification] b. Client/Company name c. All Uploaded Documents [view] [of all individual company staff] d. Requested audit date / day / time Action : 1. Allocated available Auditor for the Audit [Select] Type - Stage 2 a. View all uploaded document b. View requested date and time for audit [From client] Action :Accepted/ Rejected | 2. On-going /Past Details : a. Audit type [Verification / Certification] b. Client name c. Auditor name [Who works on that] d. Audit Stage [If Document upload stage] -->a% of completion [No. of uploaded doc vs total doc need to upload] 3. Change Audit date a. Select type [Certification / Verification] b. Client name Change Date [Button] Enter Reason [text] | 4. Add new Audit request [Admin can also add the client request that received over e-mail and call] a. Enter client/company details [Name, contact number, e-mail address,company name , ABN] b. Select Audit Type 1. Verification 2. Certification c. Select the documents to upload [Via checkbox] 1. For company 2. For Audit staff Add [Button] [Refer Sheet 2 (Document list Bist) for document list types] | 80
7 | Manage Invoice | A.View all send Invoices : 1. Invoice date and time 2. Client/company Name 3.Invoice Amount | B. Send new Invoice : 1. Select Client/Company [From drop down] 2. Select Invoice template a. Enter Deposit b. Total Amount to paid c. Audit details 3. Attach SLA Send [Button] | Note: All the Invoice will be generated by MYOB and it will record all the invoice calculation and data too. | 40
8 | Manage Transaction | 1. Transaction date and time 2. Transaction ID 3. Transaction type a. New Audit fee b. Change audit fee | 4. Audit type [[Verification/Certification]Fee] 5. Amount [X usd] 6. Client details [name, e-mail address, contact number] 7.Audit details [Auditor name[who work on that, date of audit complete]] |  | 40
9 | Manage Reports | 1. Audit Report 2. Signed SLA 3.Quote 4.Invoice Action :Export Document | Admin can also Upload New Report [pdf] a. To Client | Note : 1.All documents uploaded are deleted within 6 months after report is submitted to AU Gov 2. Admin will be notified 2 weeks before the deletion | 30
10 | Manage Content | A.Manage Resource (View/add/edit/ delete/activate/deactivate) Add new documents : 1. Title 2. Image [If any] 3. Attach document [Eg: Manuals] B. Manage Document type 1. View all document list 2. Add new Document type [Refer Sheet 2 (Document list Bist) for document type] a. Enter name | C. Notification: 1. Audit apply by new client 2. Document uploaded successfully by x client 3. Change audit date request by x client 4. Received x usd fee payment from abc client [for new audit , change audit date] 5.Document export successfully 6. Report send to client or AU govt successfully. | D. Content screens 1. About us 2.FAQ[questions ans answers] 3. Terms and conditions 4.Privacy Policy | 40
|  |  |  | Total: | 868 | 36
|  |  |  | Additional Ashish sir hours for OCR |  | 250
|  |  |  | Total hours including testing |  | 1154

## Document List Bist
For | Registration Group | Document | More info
Each audited staff | All | 100 points of ID - Primary ID document | Primary identification documents (70 points each) include: Current AHRPA Registration Birth Certificate Citizenship Certificate Current Passport Expired passport that was not cancelled and was current within the preceding two years
Each audited staff | All | 100 points of ID - Primary or Secondary ID document | Primary identification documents (70 points each) include: Current AHRPA Registration Birth Certificate Citizenship Certificate Current Passport Expired passport that was not cancelled and was current within the preceding two years Secondary identification documents (40 points each) include: Australian Drivers Licence Identification card for an Australian public employee Identification card issued by the Commonwealth, a State or Territory as evidence of entitlement to a financial benefit State or Territory issued personal identification card Student card issued by an Australian tertiary education institution
Each audited staff | All | Right to work in Australia | Citizens must provide evidence of citizenship in the form of birth certificate, citizenship certificate or passport. Non-citizens must provide a copy of their passport or ImmiCard.
Each audited staff | All | Certificate of completion of the NDIS worker orientation program
One for the company | All | Personal accident insurance or worker's compensation insurance | A certificate of currency for current insurance that meets the minimum level of cover commensurate to the scope of the provider. NDIS providers should seek professional advice as to the type and amount of insurance that is necessary.
One for the company | All | Incident Management | Describe how the provider manages incidents, or provide a copy of your incident management process, as relevant to the supports delivered for this registration group, including any relevant material provided to participants. The process must meet the requirements of the National Disability Insurance Scheme (Incident Management and Reportable Incidents) Rules 2018. The process should be relevant (proportionate) to the size and scale of the provider and to the scope and complexity of the supports being delivered.
One for the company | All | Complaints Management | Describe how the provider manages complaints, or provide a copy of your complaints process, as relevant to the supports delivered for this registration group, including any relevant material provided to participants. The process must meet the requirements of the National Disability Insurance Scheme (Complaints) Rules 2018 and follows principles of fairness and natural justice. The process should be relevant (proportionate) to the size and scale of the provider and to the scope and complexity of the supports being delivered.
One for the company | All | Risk Management | Describe or provide a copy of the providers work health and safety policies and procedures relevant to the supports delivered for this registration group, including any relevant material provided to NDIS participants. The policies and procedures should be relevant (proportionate) to the size and scale of the provider and to the scope and complexity of the supports being delivered. This document may be reviewed as required. Providers and auditors should check the NDIS Commission’s website regularly to ensure that they are complying with the current version of this document.
One for the company | All | Public Liability Insurance | A certificate of currency for current insurance that meets the minimum level of cover commensurate to the scope of the provider. Providers should seek professional advice as to the type and amount of insurance that is necessary.
One for the company | All | Professional Indemnity Insurance | A certificate of currency for current insurance that meets the minimum level of cover commensurate to the scope of the provider. Providers should seek professional advice as to the type and amount of insurance that is necessary.
Specific Qualification | 0101 Accommodation / Tenancy Assistance | Several documents possible
Specific Qualification | 0103 Assistive Products for Personal Care and Safety | Several documents possible
Specific Qualification | 0105 Personal mobility equipment | Several documents possible
Specific Qualification | 0108 Assistance with Travel/Transport Arrangements | Several documents possible
Specific Qualification | 0109 Vehicle Modifications | Several documents possible
Specific Qualification | 0111 Home Modification | Several documents possible
Specific Qualification | 0112 Assistive Equipment for Recreation | Several documents possible
Specific Qualification | 0113 Vision Equipment | Several documents possible
Specific Qualification | 0114 Community Nursing Care | Several documents possible
Specific Qualification | 0116 Innovative Community Participation | Several documents possible
Specific Qualification | 0119 Specialised Hearing Services | Several documents possible
Specific Qualification | 0120 Household Tasks | Several documents possible
Specific Qualification | 0121 Interpreting and Translation | Several documents possible
Specific Qualification | 0122 Hearing Equipment | Several documents possible
Specific Qualification | 0123 Assistive Products for Household Tasks | Several documents possible
Specific Qualification | 0124 Communication & Information Equipment | Several documents possible
Specific Qualification | 0126 Exercise Physiology & Personal Training | Several documents possible
Specific Qualification | 0127 Management of Funding for Supports in Participants Plans (Plan Management) | Several documents possible
Specific Qualification | 0128 Therapeutic Supports | Several documents possible
Specific Qualification | 0129 Specialised Driver Training | Several documents possible
Specific Qualification | 0130 Assistance Animals | Several documents possible
Specific Qualification | 0134 Hearing Services | Several documents possible
Specific Qualification | 0135 Custom Prosthetics | Several documents possible
Other | Open field to name a specific document that can be required